PROJECT PLANNING PHASE

Project Planning Template – Product Backlog, Sprint Planning, Stories, Story Points

| Date | 30 September 2026 |
| --- | --- |
| Team ID | ________________ |
| Project Name | Script-Controlled ACL – Restrict Record Access Based on Field Value |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the product backlog below to plan the ACL development work across two sprints.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Requirement Analysis | USN-1 | As an ACL administrator, I can identify the record fields that require access control. | 2 | High |
| Sprint-1 | Requirement Analysis | USN-2 | As an ACL administrator, I can identify users, roles, and departments for access decisions. | 2 | High |
| Sprint-1 | Record & Data Design | USN-3 | As an ACL administrator, I can define record fields such as department, status, and classification. | 3 | High |
| Sprint-1 | Record & Data Design | USN-4 | As an ACL administrator, I can create sample records with field values for testing. | 3 | Medium |
| Sprint-1 | ACL Rule Design | USN-5 | As an ACL administrator, I can define rules that compare user attributes with record field values. | 3 | High |
| Sprint-2 | Script Implementation | USN-6 | As the system, I can execute the ACL script when a user requests a record. | 3 | High |
| Sprint-2 | Access Decision | USN-7 | As the system, I can allow access when the user attribute matches the permitted record field value. | 3 | High |
| Sprint-2 | Access Testing | USN-8 | As an authorized user, I can access records permitted by the ACL rule. | 2 | High |
| Sprint-2 | Access Testing | USN-9 | As an unauthorized user, I am denied access when the field value does not match. | 2 | High |
| Sprint-2 | Audit & Documentation | USN-10 | As an administrator, I can record successful and denied access attempts. | 3 | Medium |
| Sprint-2 | Audit & Documentation | USN-11 | As a project team member, I can prepare the ACL demonstration and technical documentation. | 3 | Medium |

Project Tracker, Velocity & Burndown Chart (4 Marks)

Sprint tracker: The following schedule adapts the template's tracker fields to the two-sprint ACL academic project.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 13 | 6 Days | 30 Sep 2026 | 05 Oct 2026 | To be updated | To be updated |
| Sprint-2 | 16 | 6 Days | 07 Oct 2026 | 12 Oct 2026 | To be updated | To be updated |

Velocity

Total planned story points = 13 + 16 = 29

Number of sprints = 2

Planned average velocity = 29 / 2 = 14.5 story points per sprint

Average planned velocity per day (6-day sprint) = 14.5 / 6 ≈ 2.42 story points per day

Note: This is a planning value. Actual velocity should be calculated from the story points completed at the end of each sprint.

Burndown Chart

A burndown chart shows the work remaining versus time. For this ACL project, the team can update the remaining story points at the end of each working day.

| Sprint | Day | Planned Remaining Points | Actual Remaining Points |
| --- | --- | --- | --- |
| Sprint-1 | 0 | 13.0 | To be updated |
| Sprint-1 | 1 | 10.8 | To be updated |
| Sprint-1 | 2 | 8.7 | To be updated |
| Sprint-1 | 3 | 6.5 | To be updated |
| Sprint-1 | 4 | 4.3 | To be updated |
| Sprint-1 | 5 | 2.2 | To be updated |
| Sprint-1 | 6 | 0 | To be updated |
| Sprint-2 | 0 | 16.0 | To be updated |
| Sprint-2 | 1 | 13.3 | To be updated |
| Sprint-2 | 2 | 10.7 | To be updated |
| Sprint-2 | 3 | 8.0 | To be updated |
| Sprint-2 | 4 | 5.3 | To be updated |
| Sprint-2 | 5 | 2.7 | To be updated |
| Sprint-2 | 6 | 0 | To be updated |

ACL Project Flow

Requirements → Record Fields → ACL Rules → Script → Field-Value Check → Allow / Deny → Testing → Audit

References

Uploaded Project Planning Template – Project Planning Phase and Product Backlog/Sprint Tracker structure.

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts